Our Anuses are about to get fucked

---
Reality Check
- Regulator is fucked
- Implementation of PV model seems to be nowhere
  - Driver exists but cannot be tested
  - API not implemented at all
- Front-End still nowhere
- UART still nowhere
- No menu
- LCD driver still nowhere
- Housing incomplete
- Documentation in chaos
- Presentation not even started yet
- No sign of anything remotely related to verification
- Project management has generally been terrible and chaotic

---
Dependencies
HW Regulator
HW Regulator
OLED Driver
Menu
Buck Driver
Buck Driver
Test/Verification
PV Model
PV Model
UART
Front-End
Presentation
Documentation

---
Option 2
Make it presentable
Option 1
Fix Buck
- No idea what the problem is, we only have hunches
- Takes 2 weeks
- Hope it works.
- If it doesn't, we'll be back where we are now
- Focus on what we know works
- Make a working menu
- Make a working Front-End
- Focus on documentation and why our regulator failed.
- Focus on a good presentation

---
Why are we where we are now?
- Little to no communication between group members
- Insufficient leadership
- No roadmap
- Lack of motivation
- Lack of invested time into the project
- Irrelevant “Wunschziele”

---
Individual Feedback

---
We need a roadmap
Documentation
OLED Driver
UART
Presentation
Menu
Test/Verification
Front-End